## Prog
PLANT INDUSTRIAL PROGRAM SCORECARD
|  | BU : | FCM South Europ division |  |  |  | PLANT : |  |  | FCM BEAULIEU | [9 empty] | SCORE: |  |  | 15.62% | [16 empty] | 2017
PROGRAMS INDUSTRIAL KPI
OUTPUT KPI
[7 empty] | GATE 2B | [16 empty] | GATE 3 | [16 empty] | GATE 4
Plant Launch board |  |  |  | Program PSA |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  |  | N/A |  | 0% |  | N/A |  | 60% |  | 80% |  | 0% |  | 0% |  | N/A |  |  | 0% |  | 0%
|  |  |  | Program JLR |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  |  | N/A |  | N/A |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 60% |  |  | 0% |  | 0%
|  |  |  | Program TOYOTA/ RSA |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  |  | 0% |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
#REF!
#REF!
|  | INPUT KPI SAVING | [10 empty] | #REF!
[7 empty] | GATE 2B | [16 empty] | GATE 3 | [16 empty] | GATE 4
PSA PROGRAMS | [6 empty] | TCT / SWCT |  | Capacity |  | Eqpt & tooling (incl checking fixtures) list |  | PFMEA |  | MVP |  | Layout |  | Master schedule |  | Packaging incl. Shop stock |  |  | Eqpt & tooling (incl checking fixtures) reception |  | Packaging incl. Shop stock reception |  | Supplier PPAP |  | Launch book checklist |  | PT run@rate |  | Launch book checklist |  | MPT run@rate |  | Initial Samples Submitted |  |  | Launch book checklist |  | EMPT run@rate
[7 empty] | F | R | F | R | F | R | F | R | F | R | F | R | F | R | F | R |  | F | R | F | R | F | R | F | R | F | R | F | R | F | R | F | R |  | F | R | F | R
1 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | 2017-11-16 |  | past | done | 2017-07-28 | 2017-09-05 | 2017-07-28 | 2017-09-05 | 2017-10-15 |  | 2017-10-15 |  | 2017-10-20 |  |  | 2017-11-16 |  | 2017-11-16
2 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | 2018-01-16 |  | past | done | 2017-11-12 |  | 2017-11-12 |  | 2018-04-20 |  | 2018-04-20 |  | 2018-04-27 |  |  | 2018-07-30 |  | 2018-07-30
3 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | 2017-07-20 |  | past | done | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-09-23 |  | 2017-09-23 |  | 2017-10-19 |  |  | 2017-12-18 |  | 2017-12-18
4 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-09-19 |  | 2017-09-19 |  | 2017-10-19 |  |  | 2017-09-30 |  | 2017-09-30
5
6 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-10-20 |  | 2017-10-20 |  | 2018-04-05 |  |  | 2018-04-12 |  | 2018-04-12
7 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-09-18 |  | 2017-09-18 | 2017-09-18 | 2018-01-15 |  | 2018-01-15 |  |  |  |  | 2018-05-15 |  | 2018-05-15
8
9
10
11
12
JLR PROGRAMS | [6 empty] | TCT / SWCT |  | Capacity |  | Eqpt & tooling (incl checking fixtures) list |  | PFMEA |  | MVP |  | Layout |  | Master schedule |  | Packaging incl. Shop stock |  |  | Eqpt & tooling (incl checking fixtures) reception |  | Packaging incl. Shop stock reception |  | Supplier PPAP |  | Launch book checklist |  | PT run@rate |  | Launch book checklist |  | MPT run@rate |  | Initial Samples Submitted |  |  | Launch book checklist |  | EMPT run@rate
[7 empty] | F | R | F | R | F | R | F | R | F | R | F | R | F | R | F | R |  | F | R | F | R | F | R | F | R | F | R | F | R | F | R | F | R |  | F | R | F | R
1 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2016-07-08 | 2016-10-08 | 2016-07-08 | 2016-10-08 | 2017-05-24 |  | 2017-05-24 | 2017-09-25 | 2017-09-30 |  |  | 2017-06-09 |  | 2017-06-09
2 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-02-03 | 2017-04-15 | 2017-02-03 | 2017-04-15 | 2017-07-30 |  | 2017-07-30 | 2017-10-09 | 2017-09-20 |  |  | 2017-09-16 |  | 2017-09-16
3 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-06-30 | 2017-07-20 | 2017-06-30 | 2017-07-20 | 2017-06-01 |  | 2017-06-01 |  | 2017-05-30 | 2017-05-30 |  | 2017-06-23 |  | 2017-06-23
4 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-06-30 | 2017-07-20 | 2017-06-30 | 2017-07-20 | 2017-06-01 |  | 2017-06-01 | 2017-10-03 | 2017-04-20 | 2017-04-20 |  | 2017-06-23 |  | 2017-06-23
5 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | past | done | past | done | past | done | 2017-07-19 | 2017-08-20 | 2017-07-19 | 2017-08-20 | 2017-08-25 |  | 2017-08-25 |  | 2017-09-15 | 2017-09-15 |  | 2017-10-06 |  | 2017-10-06
6 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | 2017-12-18 |  | 2017-12-18 |  | 2018-01-12 |  | 2018-01-26 |  | 2018-01-26 |  | 2018-03-23 |  | 2018-03-23 |  | 2018-03-30 |  |  | 2018-08-03 |  | 2018-08-03
6
7
8
9
10
7 | [23 empty] | 2018-04-01 |  | 2018-04-01 |  | 2018-04-30 |  | 2018-06-18 |  | 2018-06-18 |  | 2018-09-03 |  | 2018-09-03 |  | 2018-09-17 |  |  | 2019-01-17 |  | 2019-01-17
[7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
TOYOTA & RENAULT PROGRAMS | [6 empty] | TCT / SWCT |  | Capacity |  | Eqpt & tooling (incl checking fixtures) list |  | PFMEA |  | MVP |  | Layout |  | Master schedule |  | Packaging incl. Shop stock |  |  | Eqpt & tooling (incl checking fixtures) reception |  | Packaging incl. Shop stock reception |  | Supplier PPAP |  | Launch book checklist |  | PT run@rate |  | Launch book checklist |  | MPT run@rate |  | Initial Samples Submitted |  |  | Launch book checklist |  | EMPT run@rate
[7 empty] | F | R | F | R | F | R | F | R | F | R | F | R | F | R | F | R |  | F | R | F | R | F | R | F | R | F | R | F | R | F | R | F | R |  | F | R | F | R
1 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | 2018-01-01 |  | 2018-01-01 |  | 2018-03-27 |  | 2018-03-13 |  | 2018-03-13 |  | 2018-05-22 |  | 2018-05-22 |  | 2018-06-19 |  |  | 2018-09-29 |  | 2018-09-29
2 | [6 empty] | past | done | past | done | past | done | past | done | past | done | past | done | past | done | past | done |  | 2017-07-20 |  | 2017-10-30 |  | 2017-10-30 |  | 2017-11-08 |  | 2017-11-08 |  | 2018-01-16 |  | 2018-01-16 |  |  |  |  | 2018-05-18 |  | 2018-05-18
3
4
4
5
6
7
8
9
10
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42936 | 0 | [10 empty] | 43116 | 0 | 0 | 0
Hélios, SAP, PPTL tools training session for newcomers PPTL
TOP 5 Action plan | [5 empty] | Pilot | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
[6 empty] | TZN | [18 empty] | ON GOING |  | DONE
[6 empty] | BLC | [18 empty] | ON GOING |  | ON GOING
[6 empty] | BLC | [18 empty] | ON GOING |  | DONE
[6 empty] | TZN | [18 empty] | ON GOING |  | ON GOING
[6 empty] | BLC | [20 empty] | ON GOING
Photo